Terms of Reference

Consultancy service

on development of Disability Inclusive Disaster Risk Reduction Plans

in 4 commune and a ward in Kon Tum city, Kon Tum province

# INTRODUCTION

With the support of the CBM CEARO, the National Institute of Agricultural Planning and Projection(NIAPP) is implementing a project namely Disability-inclusive Disaster Risk Reduction and Income Diversification for ethnic minorities of Viet Nam. The Project Goal is “To increase disaster resilient of the ethnic minorities in Viet Nam”, the Long term Objective  of the project is “Good practice of Disability Inclusive Disaster Risk Reduction and diversified income for ethnic minority in Central Highland of Viet Nam is implemented by local government and communities, and promoted nationally “.

In November 2015, the project supported the establishment of  (DRR) Technical Assistance Groups in Kon Tum city and five project communes/ward namely Doan Ket, Dak Nang, Dak Ro Wa, Chu Hreng and Thang Loi. Each group consisted three people. Those people were provided a 5-day training course on Disability Inclusive Disaster Risk Assessment in November 2015. Then, Doan Ket is the first commune that is supported in development of the commune and village DiDRR plans. A DiDRA exercise was conducted in Doan Ket commune in January 2016 and the development of village and commune DiDRR Plans is under process. It is planned that the DiDRA Plans of five villages and Doan Ket commune will be completed by the end of June 2016. The results and experiences on DiDRA and DiDRR planning in Doan Ket commune will be applied for the remaining communes/wards.

In Quarter 3 and 4 this year, the project will support four project target communes including Vinh Quang, Dak Nang, Dak Rowa, Chu Hreng and Thang Loi ward to develop Commune DiDRR Plans.

NIAPP is seeking a consultant to support four communes of Vinh Quang, Dak Nang, Dak Rowa, Chu Hreng and Thang Loi ward, Kon Tum city to develop Commune Disability Inclusive Disaster Risk Reduction Plans.

# OBJECTIVE

The objective of the consultancy is to provide technical supports to the local partners and communities in development of Commune Disability Inclusive Disaster Risk Reduction Plans in four communes and a ward mentioned above.

# METHODOLOGIES

Participatory approaches will be applied, and these approaches should ensure that Commune DiDRR Plans are inclusive for all target groups, especially the People with Disabilities.

# DELIVERABLES

- 18-20 members of Technical Assistance Group of Kon Tum city and target project communes/ward are trained on disability inclusive disaster risk management planning

- 5 Commune Hazard Maps

- 5 Commune Disability Inclusive Disaster Risk Assessment Reports

- 5 commune/ward Disability Inclusive Disaster Risk Reduction Plans

- A mission report

Language: All reports must be in both English and Vietnamese.

# CONSULTANT RESPONSIBILITIES

1/ To conduct  a 3-day training course on DiDRR planning in Kon Tum city

2/ To provide technical supports to TAGs in the following items:

- Preparation of a workplan for DiDRA and DiDRR planning

- Field work during conducting DiDRAs in 5 communes

- Preparation of commune DiDRA reports

- Facilitation of commune planning workshops

- Editing the Commune DiDRR Plans

3/ To write a mission report

# CONSULTANT REQUIREMENTS

The consultancy mission will be conducted by a consultant. The candidate has  to meet the following criteria:

- Bachelor or Master’s degree in related fields

- A strong background in disability inclusive disaster reduction

- Minimum 10 years of professional experience in disaster risk reduction management and disability

- Strong experiences on conducting inclusive Disaster Risk Reduction Assessment and DiDRR planning

- Sound knowledge and experiences on communicating with persons with disabilities and ethnic minorities.

- Persons with disabilities meeting the above requirements will be preferred as a consultant.

# DURATION AND TIMING

The assignment will be conducted in 6 months, between July and December 2016.

# MANAGEMENT

The consultants will be managed by the Project Officers.

# APPLICATION PROCEDURE

The applicants should prepare (i) A letter of interest (1 page); (ii) Technical proposal that presents how the consultant would implement this assignment, and proposed budget ; and (iii) the most updated CV.

These documents should be sent to nguyen.hai.anh.nd@gmail.com; vuthuclinh2000@gmail.com;  cc: hongnga.nguyen@cbm.org.

The deadline of the application submission is 17h00, 29 August 2016.